## Sheet1
Project Log Book - Jonathan Walsh - Project Umbra
Date | Objectives to be completed for that week | Where week's objective completed? If no, why not? | Other Issues | Productivity score (0-10) | References/Resources | Supervisor Comments/advice | Further Comments
2019-11-01 | Make engine fully object orientated; Make the architecture component-based; Implement PCF shadows | No, I ran into DirectX Errors, which where due to the fact that there where mismatches between shaders. This means that shaders that I use in future must have a similar vertex input struture to TangentVertex which includes tangents required for parallax mapping. This has meant that I have ran out of time implementing shadows at all. | Shadows aren't working at all because the if statement in the shadow shader is never being entered, this needs to be resolved asap. Once I get this working, I can then implement PCF shadows. | 5 | Stackoverflow, Games Dev | Recommended that strutures being passed to shaders should be the same to avoid DirectX errors with mismatches, although this may limit future functionality in shaders such as animations. Also mentioned that you can't have a shadow texture and render target as shown as a DirectX warning. Laurent talked about vertex buffers for each mesh and how it's not as efficent as having a global vertex buffer rather than multiple encapsulated vertex buffers. | The amount of work needs to be ramped up in order to complete all my must have objectives by christmas at the latest. All of Wednesday was spent on trying to fix DirectX errors, which meant not much got completed
2019-11-11 | Get shadows working; 'Attempt' to Implement PCF shadows; | Got shadows working. Tried to implement PCF but still have the aliasing. | Code looks messy. May cause confusion in the future. Solution: Add comments, get rid of literals, add classes, methods etc. | 7 | Stackoverflow, Games Dev
2019-11-18 | Get PCF properly working; Implement other types of light, directional and maybe area for example; Find assets for scene
2019-11-25
2019-12-02
2019-12-09
2019-12-16