## Sheet1
Project Log Book - Jonathan Walsh - Project Umbra
Date | Objectives to be completed for that week | Where week's objective completed? If no, why not? | Other Issues | Productivity score (0-10) | References/Resources | Supervisor Comments/advice | Further Comments
2019-11-01 | Make engine fully object orientated; Make the architecture component-based; Implement PCF shadows | No, I ran into DirectX Errors, which where due to the fact that there where mismatches between shaders. This means that shaders that I use in future must have a similar vertex input struture to TangentVertex which includes tangents required for parallax mapping. This has meant that I have ran out of time implementing shadows at all. | Shadows aren't working at all because the if statement in the shadow shader is never being entered, this needs to be resolved asap. Once I get this working, I can then implement PCF shadows. | 5 | Stackoverflow, Games Dev | Recommended that strutures being passed to shaders should be the same to avoid DirectX errors with mismatches, although this may limit future functionality in shaders such as animations. Also mentioned that you can't have a shadow texture and render target as shown as a DirectX warning. Laurent talked about vertex buffers for each mesh and how it's not as efficent as having a global vertex buffer rather than multiple encapsulated vertex buffers. | The amount of work needs to be ramped up in order to complete all my must have objectives by christmas at the latest. All of Wednesday was spent on trying to fix DirectX errors, which meant not much got completed
2019-11-19 | Get shadows working; 'Attempt' to Implement PCF shadows; | Got shadows working. Implemented PCF shadows | Code looks messy. May cause confusion in the future. Solution: Add comments, get rid of literals, add classes, methods etc. | 7 | Stackoverflow, Games Dev | When having multiple lights make sure the are in groups of 4. For example 1 float4 or a float3 and float etc. Try fixing as many warnings as possible as later on it would be harder to debug if these warnings are in the way too.
2019-11-26 | Get arrays working for lights being passed over to shader. Try fixing as many as the directx warnings as possible. Improve program architecture further to make programming more generic. Extra: Get assets together and setup the scene with the assets | Didn't get all warnings fixed and didn't improve architecture but got array of lights working |  | 6 |  | Supervisor advised going through code line by line to find where warnings coming from. Could be something to do with something not being set up correctly for the first model.
2019-12-03 | Get all warnings fixed. Have member variable for device context in scene class as Get calls have an overhead. Start getting assets together
2019-12-10 | Have a scene setup with house and lamps. Extra: implement variance mapping
2019-12-17